## Sheet1
DOWNSWOOD PARISH COUNCIL - ACTION PLAN
NUMBER | OBJECTIVE | ACTION | COMMITTEE/REP | UPDATES | DATE FOR FULL COUNCIL | DECISIONS FOR FULL COUNCIL | STATUS
1 | Olympicnic Event | Make necessary arrangements | Social Committee | Agreement reached on format | 2024-07-02 | To Apaprove a float for purchase of provisions | Yes Completed
2 | Christmas Event | Make necessary arrangements | Social Committee | Planning is still in progress | 2024-07-02 | To approve the repair or disposal of the lights | In progress
3 | Foxden Drive Play Area | Remove unsightly growth including brambles | Open Spaces | On going work butMBC will need to assist with the brambles | Report updates to each DPC meeting | None at present | In progress
4 | Orchard Spot Steps | Remove weeds and growth | Open Spaces | Not yet started but will seek resident volunteers | Report updates to each DPC meeting | None at present | Not Yet Started
5 | SSSI Footpath | Remove weeds and growth | Open Spaces | 07/08/24 - email sent to Natural England and waiting for a rersponse. | TBC | None at present | In Progress
6 | Kent Association for Local Councils (KALC) | To attend meetings and report to full council | KALC Lead | An on-going process as meetings occur during the year | TBC | None at present | In progress
7 | Foxden Drive Play Area | Dangerous matting and equipment to be replaced | Open Spaces | Being reviewed by MBC - waiting an update | TBC | Non at prersent | In Progress
8 | Wild Flower Areas | Autumn strimming | Open Spaces | Now strimmed | None | None at present | Yes Completed
9 | Public Seating | to review if further public benches are needed in Downswood | Open Spaces | Not yet started | TBC | None at present | In Progress
10 | Mallards | Goal Posts to be replaced | Open Spaces | MBC to replace the goal posts | TBC | None at present | Not Yet Started
11 | Grass Verges | Maintenance of grass verges throught Downswood | Open Spaces | On going for OSC, MBC and KCC | TBC | None at present | In Progress